## Gantt
VaultFive — Accelerated Project Gantt (Planned Schedule)
Planning horizon: 9–23 September 2026. Target: submission-ready by the third week of September. Planned dates must be updated against actual progress.
ID | Task / Deliverable | Owner | Start | Finish | Days | Status | Phase | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23
1 | Project setup & repository baseline | Caleb | 2026-09-09 | 2026-09-09 | 1 | In Progress | Sprint 1 | bar: 2026-09-09
2 | Sprint 1 planning & short project schedule | Caleb | 2026-09-09 | 2026-09-10 | 2 | In Progress | Sprint 1 | bar: 2026-09-09 to 2026-09-10
3 | Requirements Baseline v1 | Fardin | 2026-09-10 | 2026-09-13 | 4 | Planned | Sprint 1 | bar: 2026-09-10 to 2026-09-13
4 | User Stories & MoSCoW prioritisation | Fardin | 2026-09-11 | 2026-09-14 | 4 | Planned | Sprint 1 | bar: 2026-09-11 to 2026-09-14
5 | Risk Register v1 | Eray | 2026-09-10 | 2026-09-13 | 4 | Planned | Sprint 1 | bar: 2026-09-10 to 2026-09-13
6 | Test Plan v1 | Eray | 2026-09-11 | 2026-09-15 | 5 | Planned | Sprint 1 | bar: 2026-09-11 to 2026-09-15
7 | Initial UI/UX wireframes | Diana | 2026-09-10 | 2026-09-14 | 5 | Planned | Sprint 1 | bar: 2026-09-10 to 2026-09-14
8 | Technical architecture & proof of concept | Aaron | 2026-09-10 | 2026-09-15 | 6 | Planned | Sprint 1 | bar: 2026-09-10 to 2026-09-15
9 | Sprint 1 review & baseline approval | Team 4 / Caleb | 2026-09-16 | 2026-09-16 | 1 | Planned | Milestone 1 | bar: 2026-09-16
10 | Core desktop app integration | Aaron + Team | 2026-09-16 | 2026-09-20 | 5 | Planned | Sprint 2 | bar: 2026-09-16 to 2026-09-20
11 | Authentication / login / logout workflow | Aaron + Team | 2026-09-16 | 2026-09-20 | 5 | Planned | Sprint 2 | bar: 2026-09-16 to 2026-09-20
12 | Credential CRUD workflow | Aaron + Team | 2026-09-17 | 2026-09-21 | 5 | Planned | Sprint 2 | bar: 2026-09-17 to 2026-09-21
13 | UI implementation & accessibility review | Diana + Team | 2026-09-16 | 2026-09-21 | 6 | Planned | Sprint 2 | bar: 2026-09-16 to 2026-09-21
14 | Security/storage integration review | Aaron + Eray | 2026-09-18 | 2026-09-21 | 4 | Planned | Sprint 2 | bar: 2026-09-18 to 2026-09-21
15 | Execute functional/negative/integration tests | Eray + Team | 2026-09-19 | 2026-09-22 | 4 | Planned | Sprint 2 | bar: 2026-09-19 to 2026-09-22
16 | Defect fixing & regression testing | Team 4 | 2026-09-21 | 2026-09-23 | 3 | Planned | Sprint 2 | bar: 2026-09-21 to 2026-09-23
17 | Group report & evidence consolidation | Caleb + Team | 2026-09-17 | 2026-09-23 | 7 | Planned | Submission Prep | bar: 2026-09-17 to 2026-09-23
18 | Individual reflection drafts | All members | 2026-09-20 | 2026-09-23 | 4 | Planned | Submission Prep | bar: 2026-09-20 to 2026-09-23
19 | Final QA / submission-readiness review | Team 4 / Caleb | 2026-09-23 | 2026-09-23 | 1 | Planned | Milestone 2 | bar: 2026-09-23
Legend: Blue = planned task duration ¦ Green = milestone / one-day review

## Sprint Summary
VaultFive — Accelerated September Plan
Period | Primary Goal | Key Outputs | Lead(s) | Review Point | Planned Outcome
9–15 Sep | Sprint 1 baseline | Requirements v1; MoSCoW; risk register; test plan; wireframes; architecture/PoC | All, coordinated by Caleb | 16 Sep | Baseline ready for implementation
16–20 Sep | Core integration | Desktop app; authentication; CRUD; UI integration; storage/security review | Aaron + Team | Ongoing | Core product workflow working
21–23 Sep | Verification & submission readiness | Defect fixes; regression; evidence; report; reflection drafts; final QA | All, coordinated by Caleb | 23 Sep | Submission-ready package